## ProjectTeam
Name | GitHub Alias
Fabienne Calderara | caldf1
Florian Held | heldf1
Christian Carstens | carsc1
Nesljihan Umeri-Sali | umern11
Gian-Andrea Degen | degeg1
Tanja Nedovic | nedot1
Mamtha Sivagulanathan | nallm1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | create new/change client | A new client is entered in the system. All information needed will be put into the system. | high | 21.5
2 | create new/changing case | For treating the client a new case has to be opened. | high | 15
3 | create new/change assignement | A new assigment from the doctor is recorded by the client. | high | 15
4 | crate new/change appointment | Client needs to be visited. An appointment will be arranged by phone. The appointment will be wiritten into the calendar. | high | 20
5 | File documents | A document is sent by mail/e-mail. Documents needs to be stored in client's record. | low
6 | Searching through/looking at client's documents | Caregiver wants to inform himself/herself about the client and looks up the documents | low
7 | document/change visit | Caregiver visits client for appointment (talking, medication etc.) Caregiver documents visit. | high | 15
8 | create new/change service | After the caregiver visits client, services will be recorded | low
9 | Create bill | In case of new bills, they have to be issued at the end of the month. They need to be printed out or sent electronically. | low
10 | Looking up statistics | Caregiver wants to look at his/her stats (numeber of cases/services) and wants to send it to the Federal Office of Statistics. | low
11 | create/change prescription | Caregiver sees the need that his/her client needs further assistance and writs a prescription. The caregiver sends the prescription by mail/e-mail. | low
12 | release client's chart | Caregiver is sick/on vacation. He/she organizes a suppsitue caregiver for the meantime and has to release the client's chart for his/her suppsitue. | medium | 50
13 | create new/change network | All required contac information (people, insitutions), which are in direct contact with the client, are added. | medium | 45
14 | looking up client/list of clients | Caregiver wants to search throuh his/her list of clients to get an overview. | high | 25
15 | looking up agenda | Caregiver wants to look at his/her agenda to plan further appointmetns. | high | 15
16 | Login | Caregiver wants to login into the web application | low
|  |  | Total h | 221.5

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Layout GUIs | Create basic layout for GUIs | View | Gian-Andrea | Mamtha | high | 4 |  | 8 | done
1.2 | 1 | Client class | Implementieren logic | Model | Tanja | Fabienne | high | 3 |  | 3 | done
1.3 | 1 | Client class | Implementing GUI | View | Chris | Gian-Andrea | medium | 3 | 4 | 4 | done
1.4 | 1 | Client database | Creating first draft |  | Nesli | Tanja | high | 3 | 10 | 10 | done
1.5 | 1 | Client database | Implementing data base | Data base | Tanja | Fabienne | high | 2 | 4 | 6 | done
1.6 | 1 | Client database | Connecting data base to client class | Model, data base | Fabienne | Tanja | medium | 2 | 8 | 8 | done
1.7 | 1 | Unity test | Testing basic set-up | J-Unit | Fabienne | Florian | low | 1.5 |  |  | waiting
1.8 | 1 | Unity test | Testing for client class | J-Unit | Nesli | Tanja | low | 1 |  |  | waiting
1.9 | 1 | Unity test | Testing for client data base | J-Unit | Gian-Andrea | Mamtha | low | 1 |  |  | waiting
1.1 | 1 | Unity test | Testing for case class | J-Unit | Florian | Chris | low | 1 |  |  | waiting
1.11 | 1 | Unity test | Testing for appointment class | J-Unit | Mamtha | Florian | low | 1 |  |  | waiting
2 | 1 | Case class | Implementing logic | Model | Mamtha | Chris | medium | 3 |  |  | stopped
2.1 | 1 | Case class | Implementing GUI | View | Gian-Andrea | Nesli | low | 4 | 8 | 8 | done
4 | 1 | Appointment class | Implemting logic | Model | Chris | Nesli | high | 4 |  |  | waiting
4.1 | 1 | Appointment class | Implementing GUI | View | Chris | Gian-Andrea | medium | 2.5 |  |  | waiting
13 | 1 | Function network | Evaluating variaton of implementation | Software architecture, class diagram | Mamtha | everyone | high | 3 |  | 3 | done
13.1 | 1 | Function network | Creating first draft |  | everyone | everyone | medium | 3 |  | 3 | done
1.12 | 2 | Database class | Implementing logic for Database connection | Model, data base | Tanja | Fabienne | high | 6 | 20 | 15 | working
1.13 | 2 | Database class | Implementing logic for CRUD | Model, data base | Tanja | Fabienne | high | 6 | 12 | 15 | working
1.14 | 2 | Database class | Creating Connection between program and database | Model, data base | Florian | Tanja | high | 6 | 10 | 10 | working
1.15 | 2 | Address Class | Implementing logic | Model | Nesli | Mamtha | high | 4 |  | 8 | done
16 | 2 | Caregiver Class | Implementing logic | Model | Nesli | Mamtha | high | 3 |  | 5 | done
1.16 | 2 | Communication Class | Implementing logic | Model | Nesli | Mamtha | high | 3 |  | 7 | done
13.2 | 2 | Contact Class | Implementing logic | Model | Nesli | Mamtha | high | 4 |  | 5 | done
13.3 | 2 | ExternalInstitution Class | Implementing logic | Model | Mamtha | Nesli | high | 4 |  | 6 | done
1.17 | 2 | Person Class | Implementing logic | Model | Mamtha | Nesli | high | 4 |  | 5 | done
13.4 | 2 | ExternalPerson Class | Implementing logic | Model | Mamtha | Nesli | high | 3 |  | 7.5 | done
1.18 | 2 | Client Class | Implementing GUI, multiple Views | View | Gian-Andrea | Chris | high | 6 | 12 | 12 | done
13.5 | 2 | Network Class | Implementing GUI | View | Gian-Andrea | Chris | high | 8 | 12 | 12 | done
2.2 | 2 | Case class | Implementing GUI, multiple Views | View | Gian-Andrea | Chris | high | 6 | 10 | 10 | done
8 | 2 | Activity Reporting class | Implementing logic | Model | Florian | Mamtha | low | 4 |  | 6 | done
4.2 | 2 | Appointment class | Implementing logic | Model | Florian | Mamtha | low | 4 |  | 4 | done
9 | 2 | Bill class | Implementing logic | Model | Fabienne | Nesli | low | 4 |  | 5 | done
15 | 2 | Calender class | Implementing logic | Model | Fabienne | Nesli | low | 6 |  | 6 | done
10 | 2 | Statistics class | Implementing logic | Model | Chris | Gian | low | 6 |  | 4 | working
7 | 2 | Meddoku class | Implementing logic | Model | Chris | Tanja | low | 5 |  | 5 | done
1.19 | 2 | All Classes | Changing structure | Model, View, data base | Fabienne | Florian | high | 6 |  | 10 | done
1.7 | 3 | Unity test | Testing basic set-up | J-Unit | Fabienne | Florian | low | 4 |  | 8 | done
1.8 | 3 | Unity test | Testing for client class | J-Unit | Nesli | Tanja | low | 4 |  | 6 | done
1.9 | 3 | Unity test | Testing for client data base | J-Unit | Gian-Andrea | Mamtha | low | 4 |  | 6 | done
1.1 | 3 | Unity test | Testing for case class | J-Unit | Florian | Chris | low | 4 |  | 6 | done
1.11 | 3 | Unity test | Testing for appointment class | J-Unit | Mamtha | Florian | low | 4 |  | 6 | done
1.12 | 3 | Database class | Implementing logic for Database connection | Model, data base | Tanja | Fabienne | high | 10 | 6 | 6 | done
1.13 | 3 | Database class | Implementing logic for CRUD | Model, data base | Tanja | Fabienne | high | 6 |  | 8 | done
1.14 | 3 | Database class | Creating Connection between program and database | Model, data base | Florian | Tanja | high | 6 |  | 8 | done
1.1 | 3 | Layout GUIs | Adapting GUI for smartphone | View | Gian-Andrea | Mamtha | high | 10 |  | 6 | done
13 | 3 | Function network | Implementing logic | Model | Mamtha | Fabienne | high | 8 |  | 7 | done
1 | 3 | Optimse Code | for all classes | all | Fabienne | everyone | high | 10 | 20 | 10 | done
1 | 3 | Controller class | Implementing logic | Controller | Fabienne | Nesli | high | 10 |  |  | waiting
[7 empty] | Total h Sprint 1 | 42 |  | 53
[7 empty] | Total h Sprint 2 | 98 |  | 142.5
[7 empty] | Total h Sprint 3 | 70 |  | 117
[7 empty] | Total h |  |  | 312.5

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2016-12-02 | 42 | 42
1 | 2016-12-08 | 35 | 21
1 | 2016-12-09 | 29 | 0
Sprint | Time of Record | Remaining Effort | Remaining Ressources
2 | 2016-12-09 | 98 | 97
2 | 2016-12-15 | 93 | 85
2 | 2016-12-16 | 92 | 81
2 | 2016-12-22 | 69 | 30
2 | 2016-12-23 | 44 | 0
Sprint | Time of Record | Remaining Effort | Remaining Ressources
3 | 2016-12-23 | 70 | 69
3 | 2016-12-28 | 68 | 53
3 | 2017-01-06 | 50 | 36
3 | 2017-01-19 | 11 | 0
Sprint 3